## Sheet1
Project Title:
Group Members:
Subtask | Start time | Length of task | Progess %
Scope document | 0 | 2 | 100%
Feasability Study | 2 | 2 | 50%
Introduction screen | 4 | 1 | 0
Game | 5 | 10 | 0
Game over screen | 15 | 1 | 0
Encapsulation | 16 | 1 | 0
User guide | 17 | 1 | 0
Testing | 18 | 1 | 0
Reflection report | 19 | 1 | 0