## GanttChart
Gantt Chart | [8 empty] | © 2008 Vertex42 LLC | 0
FSE Game
Boomnack
| Project Lead: | Adam Vandolder
| Today's Date: | 2016-06-03 | 2016-06-03 | (vertical red line)
[42] | Start Date: | 2016-06-03 | 2016-06-03 | [5 empty] | First Day of Week (Sun=1): | 2 | 2016-05-30 | 2016-05-31 | 2016-06-01 | 2016-06-02 | 2016-06-03 | 2016-06-04 | 2016-06-05 | 2016-06-06 | 2016-06-07 | 2016-06-08 | 2016-06-09 | 2016-06-10 | 2016-06-11 | 2016-06-12 | 2016-06-13 | 2016-06-14 | 2016-06-15 | 2016-06-16 | 2016-06-17 | 2016-06-18 | 2016-06-19 | 2016-06-20 | 2016-06-21 | 2016-06-22 | 2016-06-23 | 2016-06-24 | 2016-06-25 | 2016-06-26 | 2016-06-27 | 2016-06-28 | 2016-06-29 | 2016-06-30 | 2016-07-01 | 2016-07-02 | 2016-07-03
WBS | Tasks | Task Lead | Start | End | Duration (Days) | % Complete | Working Days | Days Complete | Days Remaining | 2016-05-30: 2016-05-30; 2016-06-06: 2016-06-06; 2016-06-13: 2016-06-13; 2016-06-20: 2016-06-20; 2016-06-27: 2016-06-27
1 | Stage 1 |  | 2016-06-02 | 2016-06-15 | 20 | 100% | 10 | 20 | 0
1.1 | Scope document |  | 2016-06-02 | 2016-06-02 | 1 | 100% | 1 | 1 | 0
1.2 | Feasability Study |  | 2016-06-03 | 2016-06-07 | 3 | 100% | 3 | 3 | 0
1.3 | Introduction screen |  | 2016-06-08 | 2016-06-09 | 1 | 100% | 2 | 1 | 0
1.4 | Game |  | 2016-06-10 | 2016-06-20 | 10 | 100% | 7 | 10 | 0
1.5 | Game over screen |  | 2016-06-21 | 6/21/16 | 1 | 100% | 1 | 1 | 0
1.6 | Encapsulation |  | 2016-06-22 | 2016-06-22 | 1 | 100% | 1 | 1 | 0
1.7 | User guide |  | 2016-06-23 | 2016-06-23 | 1 | 100% | 1 | 1 | 0
1.8 | Testing |  | 2016-06-24 | 2016-06-24 | 1 | 100% | 1 | 1 | 0
1.9 | Reflection report |  | 2016-06-25 | 2016-06-25 | 1 | 100% | 0 | 1 | 0
Note on J1: Limited Use Policy You may download this template ("Software") free of charge, make archival copies, and customize the Software for personal use only. This Software or any document including or derived from this Software may NOT be sold, distributed, or placed on a public server such as the internet without the express written permission of Vertex42 LLC. You may not remove or alter any logo, trademark, copyright, hyperlinks, disclaimers, terms of use, or other proprietary notices within the Software. We define "Personal use" as Non-Commercial use by you, your family, or by your close personal friends, on a computer not owned by a business or commercial entity. We define "Commercial use" as any use in which a corporation or business or commercial entity derives or attempts to derive monetary gain and benefit, either directly or indirectly, from the use of the Software. This includes Government and Military entities, corporations, LLCs, sole-proprietorships, home-based businesses, and internet-based businesses. No Warranties THE SOFTWARE AND ANY RELATED DOCUMENTATION ARE PROVIDED TO YOU "AS IS." VERTEX42, LLC MAKES NO WARRANTIES, EXPRESS OR IMPLIED, AND EXPRESSLY DISCLAIMS ALL REPRESENTATIONS, ORAL OR WRITTEN, TERMS, CONDITIONS, AND WARRANTIES, INCLUDING BUT NOT LIMITED TO, IMPLIED WARRANTIES OF MERCHANTABILITY, FITNESS FOR A PARTICULAR PURPOSE, AND NONINFRINGEMENT. WITHOUT LIMITING THE ABOVE YOU ACCEPT THAT THE SOFTWARE MAY NOT MEET YOUR REQUIREMENTS, OPERATE ERROR FREE, OR IDENTIFY ANY OR ALL ERRORS OR PROBLEMS, OR DO SO ACCURATELY. This Agreement does not affect any statutory rights you may have as a consumer. Limitation of Liability IN NO EVENT SHALL VERTEX42, LLC BE LIABLE TO YOU, FOR ANY DAMAGES, INCLUDING ANY LOST PROFITS, LOST SAVINGS, OR ANY OTHER DIRECT, INDIRECT, SPECIAL, INCIDENTAL, OR CONSEQUENTIAL DAMAGES ARISING FROM THE USE OR THE INABILITY TO USE THE SOFTWARE (EVEN IF WE OR AN AUTHORIZED DEALER OR DISTRIBUTOR HAS BEEN ADVISED OF THE POSSIBILITY OF THESE DAMAGES), OR ANY MISTAKES AND NEGLIGENCE IN DEVELOPING THIS SOFTWARE, OR FOR ANY CLAIM BY ANY OTHER PARTY. THE ORGANIZATION, BUSINESS, OR PERSON USING THIS SOFTWARE BEARS ALL RISKS AND RESPONSIBILITY FOR THE QUALITY AND PERFORMANCE OF THIS SOFTWARE. Somes states do not allow the limitation or exclusion of liability for incidental or consequential damages, so the above limitation may not apply to you.
Note on A9: Work Breakdown Structure Enter the Task# and Subtask# 2 2.1 2.2 etc.
Note on D9: Start Date Enter the starting date for this task. To associate the start date with the end of another task, enter a formula in the start date that refers to the end date of that task.
Note on E9: End Date The ending date is calculated by adding the Duration (calendar days) to the Start date minus 1 day, because the task duration is from the beginning of the Start day to the end of the End day.
Note on F9: Duration (Calendar Days) Enter the number of calendar days for the given task. Refer to the Working Days column or use a calendar to determine the corresponding working days. For the main tasks, you can calculate the duration by finding the maximum End date of the sub tasks and subtracting the earliest start date. For example: F11=MAX(E12:E15)-D11
Note on G9: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%). For the main tasks, you can use a weighted average of the sub tasks by adding the formula: G11=SUMPRODUCT(F12:F15,G12:G15)/SUM(F12:F15) Note: If you insert rows, make sure that the calculation is updated correctly.
Note on H9: Working Days Counts only Mon-Fri, using the NETWORKDAYS() formula. When planning work based upon the number of working days, adjust the Duration until the desired # of working days is reached. Note: If the start date is later changed, the number of working days may also change.
Note on I9: Calendar Days Complete This column is calculated by multiplying the Duration by the %Complete and rounding down to the nearest integer.
Note on J9: Calendar Days Remaining This column is calculated by subtracted the Days Complete from the Duration.